## Sheet1
PRODUCT BACKLOG REPORT
ID | MODULES | USER STORY | PRIORITY | COMPLEXITY | ESTIMATION | STATUS | STATUS | PRIORITY
US01 | User Management | As a new user, I want to register with my email and password, so that I can create an account and access the application. | HIGH | HIGH | 40 | In Progress | Not Started | High
|  | As an existing user, I want to log in with my email and password, so that I can access my account and use the application's features. | HIGH | MEDIUM |  | In Progress | In Progress | Medium
|  | As an admin, I want to manage user accounts, so that I can maintain the integrity of the user database. | MEDIUM | MEDIUM |  | In Progress | Complete | Low
US02 | Ride Matching | As a user, I want to find and match with rides that are heading in the same direction, so that I can share a ride and reduce my travel costs. | HIGH | MEDIUM | 15 | Not Started | Overdue
|  | As a driver, I want to see potential riders who are on my route, so that I can fill my car and maximize my earnings. | HIGH | MEDIUM |  | Not Started | On Hold
US03 | Fare Calculation | As a user, I want to see the estimated fare for my ride before booking, so that I can make an informed decision. | MEDIUM | MEDIUM | 20 | Not Started
|  | As a driver, I want to know how much I will earn from a ride, so that I can plan my trips efficiently. | MEDIUM | MEDIUM |  | Not Started
US04 | Trip Management | As a user, I want to create, update, and delete my trips, so that I can manage my travel plans. | HIGH | HIGH | 35 | Not Started
|  | As a driver, I want to manage my offered rides, so that I can keep track of my ride schedules. | MEDIUM | MEDIUM |  | Not Started
US05 | Payment Service | As a user, I want to securely pay for my rides using various payment methods, so that I can complete transactions effortlessly. | HIGH | HIGH | 40 | Not Started
|  | As a driver, I want to receive payments for my rides directly into my bank account, so that I can get compensated promptly. | MEDIUM | MEDIUM |  | Not Started
|  | As a user, I want to view my payment history, so that I can track my expenses. | MEDIUM | MEDIUM |  | Not Started
|  | As an admin, I want to manage and resolve payment disputes, so that I can ensure smooth financial operations. | MEDIUM | MEDIUM |  | Not Started
US06 | Frontend | As a user, I want an intuitive interface to register, log in, and manage my rides, so that I can navigate the application easily. | MEDIUM | MEDIUM | 45 | Not Started
|  | As a user, I want to track my ride in real-time and receive notifications, so that I stay informed about my ride status. | MEDIUM | HIGH |  | Not Started
US07 | Deployment | As a DevOps engineer, I want to set up and configure Kubernetes clusters, so that I can deploy microservices efficiently. | MEDIUM | MEDIUM | 15 | Not Started
|  | As a DevOps engineer, I want to deploy microservices to AWS, so that the application is scalable and reliable. | MEDIUM | MEDIUM |  | Not Started
US08 | Additional Services | As a user, I want to receive notifications about ride updates, so that I am always informed. | LOW | HIGH | 25 | Not Started
|  | As an admin, I want to view user activity reports & reviews, so that I can monitor the application's performance. | LOW | LOW |  | Not Started
|  | As a user, I want to leave reviews and ratings for my rides, so that I can share my experience with others. | LOW | LOW |  | Not Started